**Local Program**

**WEEKLY CONSTRUCTION UPDATE**

***Please return this form to the Sponsor, WisDOT Project Manager, & Supervisor, Jim Thompson (***[james.thompson@dot.wi.gov](mailto:james.thompson@dot.wi.gov)***) and NE Region Communication Specialist, Mark Kantola (***[mark.kantola@dot.wi.gov](mailto:mark.kantola@dot.wi.gov)***) no later than noon on Thursday updating work activities for the current week and upcoming week for each of your NE Region Local Program project(s).***

**Dates Covered:** July 11 – July 22

**Project ID:** 4656-06-71

**Project Name:** T Buchanan, Emons Road

**Schedule:** April 25th 2022 to October 2022

**Project Cost:** $3,220,359.29

**Location/terminals:** Pinecrest Blvd – CTH N, Town of Buchanan, Outagamie County

**Description of overall work:** This project will include the total reconstruction of Emons Road. The roadway will include 2 – 12-foot asphalt driving lanes, 2 – 5-foot asphalt bike lanes, curb & gutter and 5-foot sidewalks. New storm sewer will be installed promoting drainage.

**This week’s work:** The contractor will be installing storm sewer between Ridgewood Court and CTH N. The contractor will be placing sidewalk and driveway aprons from Woodstock Lane to Ridgewood Court. The contractor will also be placing curb & gutter from Pinecrest Boulevard to Berken Street.

**Next week’s work:**  The contractor will be installing storm sewer between Randy’s Lane and CTH N. The contractor will be placing sidewalk and driveway aprons from Pinecrest Boulevard to Ridgewood Court.

**Traffic impacts:** Emons Road will be closed to “Through Traffic”.

**Special information of interest needed by the public concerning this project:**

**Name of person providing Weekly Construction updates AND photographs of project bi-monthly once the project begins  
Name:** Scott Hintz  
**E-mail:** s.hintz@gremmerassociates.com  
**Phone #:** 715-572-7420