**Local Program**

**WEEKLY CONSTRUCTION UPDATE**

***Please return this form to the Sponsor, WisDOT Project Manager, & Supervisor, Jim Thompson (***james.thompson@dot.wi.gov***) and NE Region Communication Specialist, Mark Kantola (***mark.kantola@dot.wi.gov***) no later than noon on Thursday updating work activities for the current week and upcoming week for each of your NE Region Local Program project(s).***

**Dates Covered:** September 26 – October 7

**Project ID:** 4656-06-71

**Project Name:** T Buchanan, Emons Road

**Schedule:** April 25th 2022 to October 2022

**Project Cost:** $3,220,359.29

**Location/terminals:** Pinecrest Blvd – CTH N, Town of Buchanan, Outagamie County

**Description of overall work:** This project will include the total reconstruction of Emons Road. The roadway will include 2 – 12-foot asphalt driving lanes, 2 – 5-foot asphalt bike lanes, curb & gutter and 5-foot sidewalks. New storm sewer will be installed promoting drainage.

**This week’s work:** The contractor will landscape from Main Street to CTH N. The contractor will pave asphalt from Pinecrest Boulevard to CTH N.

**Next week’s work:**   The contractor will install signs from Pinecrest Boulevard to CTH N. The contractor will landscape from Main Street to CTH N. The contractor will install the pavement marking throughout the project.

**Traffic impacts:** Emons Road will be closed to “Through Traffic”.

**Special information of interest needed by the public concerning this project:**

**Name of person providing Weekly Construction updates AND photographs of project bi-monthly once the project begins
Name:** Scott Hintz
**E-mail:** s.hintz@gremmerassociates.com
**Phone #:** 715-572-7420